## Sheet1
DERBY LOFTS MAINTENANCE ITEMS-UPDATED AS ITEMS COME BEFORE THE BOARD
PROJECT | NOTES | POTENTIAL REPAIR | ESTIMATE RECEIVED
ELEVATORS | Otis is becoming more expensive. | 2028 | 100,000 from Otis in 2024
Board will investigate alternatives
when time to replace
HVAC | Replace Freon with Puron to reduce cost | 2020 | $40,000 at time of request in 2020
This project was not begun due to COVID
Currently put on the back-burner awaiting the
cost for completing the Masonry and Lintel
Projects.
ROOF | Still viable but should be replaced along
| with the wood walkways. | 2030 | N/A
SKYLIGHTS | We anticipate the repair/replacement of the
| building skylights will be part of the roof repair | 2030 | N/A
COMMON AREAS | On-going maintenance/painting |  | Annual Budget Item
LOBBY FLOORS | Needs a professional cleaning | 2025 | Getting Estimates
BACK FLOW VALVE | Replaced in 2023 | Keep Watch | N/A
FIRE ALARMS | On-going maintenance | Annually | Annual Budget Item
FIRE EXTINGUISHERS | On-going maintenance | Annually | Annual Budget Item
DRIVE-THRU GATES | On-going maintenance |  | Not budgeted/by incident
LOBBY DOORS | On-going maintenance |  | Not budgeted/by incident
ENTRY SYSTEM | No issues |  | Unlikely needs to be replaced
BUILDING MASONRY | Architectural Study in 2008 with | 2018 | Unknown
no action except some selected
changes being made to four units
Some unit owners were offered a deal
on new windows.
| Subsequent architectural review | 2024 | $190,000 for masonry work
pointed out that the masonry needed
immediate attention with many leaks being
reported by residents. Board committed
to the project and assessed the owners a
pro-rata share of the cost.
BUILDING LINTELS | New project from the architectural review | 2025 | 649000
in 2024. Repairs will be done on the
East side (Central Street) immediately and
will wait for building additional funds to do
the remainder of the building.
An additional assessment will be made to
fund this project